## Slide 1: Project Management
The Organization
and
the Manager

## Slide 2
Management
the art of getting things done through people
of achieving defined goals in a span of time using predefined resources

## Slide 3: Project Management
the “planning, monitoring and control of all aspects of a project and the motivation of all those involved in it to achieve the project objectives on time and to the specified cost, quality and performance

## Slide 4: HOW do we manage a Project? Who manages a Project?

## Slide 5: Organizing to create the tool for Project Management
What do we organize?

## Slide 6: Organization – is a social arrangement which pursues: - collective goals - controls its own performance - has a boundary separating it from its environment. The word itself is derived from the Greek word ὄργανον (organon) meaning tool.

## Slide 7: Now that we have the ORGANIZATION, do we now have as well the Project Management Tool?
Can the organization manage the Project?

## Slide 8: What is the Organizational Structure?
determine the modes in which the organization operates and performs
affects organizational action by:
  1) it provides the foundation on which standard operating procedures and routines rest;
  2) it determines which individuals get to participate in which decision-making processes, and thus to what extent their views shape the organization’s actions

## Slide 9: Organizational Structure
Divergence in the set organizational structure and the actual operations decreases performance of a growing organization
Organizational structures must be adaptive to process requirements, aiming to optimize the ratio of effort and input to output.

## Slide 10
Organizational Structure
What is the structure for?
What are the typical structures?
Issues on transparency (who’s doing what and why?)

## Slide 11
Organizational Structure
Leadership and membership (who are in the structure)
Decision making (who makes decision and how is decision made?)

## Slide 12: Project Management
is about how we make sure that scope is fulfilled and that we stay on time and within budget thru…

## Slide 13: Monitoring
Which is a CONTINUOUS process….not done at the end but throughout the project.
This is how you Manage the Project.

## Slide 14
  Scope
  Build or implement as per the plan or drawings. Will it achieve the set goals?
    Track by marking off tasks or updating drawings “As Builts”
Why
In/Out of Scope
Change in scope due to budget/ schedule or demands of community
Does it still meet the goals and objectives, Does the benefit increase/decrease

## Slide 15
  Budget
  Keep within allocations
  Do not run out of Money before the project is completed
  Transparency
    Track with spreadsheet or charts showing budget and money spent
Budget
Over /Under
Move Money around so that final budget still within allowance
Need more money or change scope

## Slide 16: Implementation of the Plan
Schedule
  Projects are time-bound: Follow timelines
  Identify and celebrate milestones
  Extended time in community projects, not delivering service results in loss of confidence by those participating.
    Track with a Gantt Chart
Schedule
On Time/Late
End date moved due to weather, bad planning, resource shortage or other issues
Acceleration strategies, more resources, change plan, new schedule

## Slide 17
Acc No. | Descripton | Cost Estimate Section |  |  |  | Committed | Estimated | Estimated | Difference | Comments
 |  | Quantity | Unit | Unit Price | Total | Cost | Left | total | From Budget | 
1000 | Intake Box Materials |  |  |  | 20547 |  |  | 19789 | -878 | Orginal est 18525 (inflation)
1001 | Cement | 12 | 40kg sack | 149 | 1788 | 2640 | 0 | 2640 | 852 | canvass solano 2004
1002 | Sand | 40 | cans | 41 | 1640 | 1200 | 400 | 1600 | -40 | Original estimate
1003 | Gravel | 80 | cans | 41 | 3280 | 3000 | 0 | 3000 | -280 | Original estimate
1004 | Boulder | 3 | cubc m | 800 | 2400 | 0 | 2400 | 2400 | 0 | Original estimate
1005 | sahara | 12 | bag | 22 | 264 | 600 | 0 | 600 | 336 | canvass solano 2004
1006 | Re-Bar-10mm | 15 | pcs | 96 | 1440 |  | 1500 | 1500 | -60 | canvass solano 2004
1007 | Tie Wire #16 | 2 | kg | 43 | 86 | 100 | 0 | 100 | 14 | canvass solano 2004
1008 | Lumber 1"x12"x10' (10 pcs) | 100 | bd ft | 35 | 3500 | 1500 | 1500 | 3000 | -500 | canvass solano 2004
1009 | Lumber 1"x12"x12' (10 pcs) | 120 | bd ft | 35 | 4200 | 1000 | 2000 | 3000 | -1200 | canvass solano 2004
1010 | Lumber 2"x2"x12' (15 pcs) | 60 | bd ft | 25 | 1500 |  | 1500 | 1500 | 0 | canvass solano 2004
1011 | Nails etc. (4", 2 1/2") | 3 | kg | 40 | 120 |  | 120 | 120 | 0 | canvass solano 2004
1012 | 1 1/2" x 200mm Gi Nipple | 3 | pcs | 90 | 270 |  | 270 | 270 | 0 | canvass solano 2004
1013 | 1 1/2" Elbow | 1 | pcs | 40 | 40 |  | 40 | 40 | 0 | canvass solano 2004
1014 | 1 1/2" Plug | 1 | pcs | 19 | 19 |  | 19 | 19 | 0 | canvass solano 2004

## Slide 18
  Track by filling in the Bars as you progress.
  As you progress move the dates to reflect what will happen.
  Add Resources etc to get back on schedule

## Slide 19: Reporting
Informing stakeholders on progress and issues. Leads to Transparency and Accountability
Allows the Project Manager to step back from the details and gauge real progress. “can’t see the forest for the trees”
Needs to be done at regular intervals, weekly to monthly depending on project.

## Slide 20
Project Implementation – requires resources and decisions either from several stakeholders in the organization or from 1 person, the PROJECT MANAGER

## Slide 21: Project Manager
Individual person that must be able to:
  Collect all the relevant information
  Make decisions
  Communicate with all parties to ensure that the process remains transparent
  Resolve conflict

## Slide 22: Risk Management
A Successful Project:
  Doesn’t run out of money
  Is completed on time and fulfills the goals
  Happy beneficiaries
Despite having the best plans issues will arise affecting project outcome. As you continuously monitor these will surface.

## Slide 23
Project Manager’s job is to make decisions to overcome these challenges.
  Over budget
  Late completion
  Project not working as designed
  Changes in scope
  Reduced community participation

## Slide 24
Decisions though will require:
  Gathering of Information through monitoring
  Talking to Stakeholders, conflict resolution
  Analysis of issue and options
  Making decision in a timely manner
  Explain decision to all stakeholders

## Slide 25
Bad Decisions result from
  Not enough information on the cause of issues
  Not enough research into possible solutions
  Personal feelings impacting judgment
  Decisions made either too quick or too slow

## Slide 26
Bad Decisions are NOT the end of the world
  If you realize you are wrong then you can fix it
  Learn from your mistakes.
  Be accountable and don’t try to cover up. This will only make the issue worse.

## Slide 27: Why be a Project Manager
It is not an easy job. It involves knowing all aspects of the project, working with people, resolving possible conflicts between stakeholders and being responsible for implementing necessary projects for your community.

## Slide 28: Why be a Project Manager
HOWEVER;
By using monitoring and evaluation techniques you will MINIMIZE your RISK of failure, allowing the project to be completed as it was designed, on time and within budget.

## Slide 29
Thank you!